## Sheet1
East Area Schedule v2.1.1 :: Beamlines T8, T9, T10, T11 & nToF :: Status 2023-10-06 20:00 (UTC)
Schedule Run
The scheduled runs presented in this file result from applying the following filters:
Beamlines |  | Only runs which have been scheduled in either of the beamlines "T10, T11, T8, T9, TT42" are included below.
Associated Month | Associated Week | Activity | Run name | Start Weekday | Start Date | Duration [days] | Location | Status | Usage
March | Week 13 | n_TOF | Ramp-up and beam setup | Monday | 2023-04-03 | 7 | TT42 | Scheduled | No beam (access only)
April | Week 14 | IRRAD_CHARM | EA-IRRAD proton run | Friday | 2023-04-07 | 194 | T8 | Scheduled | Main user
April | Week 14 | PAN | Low energy electrons/protons | Friday | 2023-04-07 | 14 | T9 | Scheduled | Main user
April | Week 14 | ALICE_ITS3 | PS Run April | Friday | 2023-04-07 | 7 | T10 | Scheduled | Main user
April | Week 14 | n_TOF | Physics run | Monday | 2023-04-10 | 203 | TT42 | Scheduled | Main user
April | Week 15 | ALICE_TOF | ALICE_TOF_fast_timing_1 | Friday | 2023-04-14 | 10 | T10 | Scheduled | Main user
April | Week 15 | CLOUD | CLOUD16T | Monday | 2023-04-17 | 28 | T11 | Scheduled | Main user
April | Week 16 | MEDIPIX | Medipix (PS) | Friday | 2023-04-21 | 5 | T9 | Scheduled | Main user
April | Week 16 | PAN | Low energy electrons/protons | Friday | 2023-04-21 | 5 | T9 | Scheduled | Parasitic user
April | Week 16 | ALICE_TOF | ALICE_TOF_fast_timing_1 | Monday | 2023-04-24 | 9 | T10 | Scheduled | Main user
April | Week 17 | LHCB_ECAL | Test of tracking system | Wednesday | 2023-04-26 | 7 | T9 | Scheduled | Main user
May | Week 18 | ALICE_ITS3 | PS Run for May | Wednesday | 2023-05-03 | 7 | T10 | Scheduled | Main user
May | Week 19 | CALICE_SCW_AHCAL | CALICE ScW-ECAL + AHCAL at PS (T9) | Tuesday | 2023-05-16 | 15 | T9 | Scheduled | Main user
May | Week 22 | ATLAS_MALTA | Run no. 0 for Beam request in ... | Wednesday | 2023-05-31 | 7 | T9 | Scheduled | Main user
May | Week 22 | ALICE_MUON_ID | muonID | Monday | 2023-06-05 | 2 | T10 | Scheduled | Main user
June | Week 23 | ALICE_FOCAL | PS | Wednesday | 2023-06-07 | 7 | T9 | Scheduled | Main user
June | Week 23 | ALICE_MUON_ID | muonID | Wednesday | 2023-06-07 | 14 | T10 | Scheduled | Main user
June | Week 24 | NANOCAL | NanoCal run | Wednesday | 2023-06-14 | 7 | T9 | Scheduled | Main user
June | Week 24 | HIKE_SAC | HIKE SAC 2023 | Wednesday | 2023-06-14 | 7 | T9 | Scheduled | Parasitic user
June | Week 25 | MUONE_ECAL | MUONE ECAL calibration at low energy | Wednesday | 2023-06-21 | 6 | T9 | Scheduled | Main user
June | Week 25 | IDEA_CC | LowMomentum | Wednesday | 2023-06-21 | 14 | T10 | Scheduled | Main user
June | Week 25 | MUONE_ECAL | MUONE ECAL calibration at low energy | Tuesday | 2023-06-27 | 1 | T9 | Scheduled | Main user
June | Week 26 | IDEA_DRC | Test of dual-readout calorimeter ... | Wednesday | 2023-06-28 | 14 | T9 | Scheduled | Main user
July | Week 27 | ALICE_ITS3 | PS Run June | Wednesday | 2023-07-05 | 7 | T10 | Scheduled | Main user
July | Week 27 | ALICE_TIMING | Alice3 Timing run 1 | Wednesday | 2023-07-05 | 14 | T10 | Scheduled | Parallel user
July | Week 28 | WCTE | Lower momentum beam survey measurements | Wednesday | 2023-07-12 | 6 | T9 | Scheduled | Main user
July | Week 28 | ALICE_ITS3 | PS Run July | Wednesday | 2023-07-12 | 7 | T10 | Scheduled | Main user
July | Week 28 | WCTE | Lower energy tagged photon measurements | Tuesday | 2023-07-18 | 6 | T9 | Scheduled | Main user
July | Week 29 | BL4S | Test of Equipment, Validation of Concept | Wednesday | 2023-07-19 | 7 | T10 | Scheduled | Main user
July | Week 29 | WCTE | Higher energy tagged photon measurements | Monday | 2023-07-24 | 2 | T9 | Scheduled | Main user
July | Week 30 | WCTE | Higher momentum beam survey setup | Wednesday | 2023-07-26 | 7 | T9 | Scheduled | Main user
July | Week 30 | BL4S | Test of Equipment, Validation of Concept | Wednesday | 2023-07-26 | 7 | T10 | Scheduled | Main user
August | Week 31 | TECHNO_CLS | TECHNO-CLS-PS-2023 | Wednesday | 2023-08-02 | 14 | T9 | Scheduled | Main user
August | Week 31 | ALICE_TOF | ALICE_TOF_fast_timing_2 | Wednesday | 2023-08-02 | 3 | T10 | Scheduled | Main user
August | Week 31 | ALICE_TOF | ALICE_TOF_fast_timing_2 | Saturday | 2023-08-05 | 10 | T10 | Scheduled | Main user
August | Week 32 | ALICE_ITS3 | PS Run August | Tuesday | 2023-08-15 | 7 | T10 | Scheduled | Main user
August | Week 33 | NP06_ENUBET | ENUBET | Wednesday | 2023-08-16 | 14 | T9 | Scheduled | Main user
August | Week 33 | EP_3DET | 3DET | Wednesday | 2023-08-16 | 14 | T9 | Scheduled | Parasitic user
August | Week 33 | EIC_DRICH | EIC dRICH test beam at PS | Tuesday | 2023-08-22 | 8 | T10 | Scheduled | Main user
August | Week 35 | RE44_HERD | HERD PS Proton run | Wednesday | 2023-08-30 | 14 | T9 | Scheduled | Main user
August | Week 35 | MPGDCAL | Explorative Run to test equipment ... | Wednesday | 2023-08-30 | 7 | T10 | Scheduled | Main user
September | Week 36 | RE7_GAMMA_MEV | GammaMeV | Wednesday | 2023-09-06 | 7 | T10 | Scheduled | Main user
September | Week 37 | VLAST | VLAST low energy electron run | Wednesday | 2023-09-13 | 7 | T9 | Scheduled | Main user
September | Week 37 | BL4S | Winning teams testbeam | Wednesday | 2023-09-13 | 14 | T10 | Scheduled | Main user
September | Week 37 | CLOUD | CLOUD16 | Monday | 2023-09-18 | 42 | T11 | Scheduled | Main user
September | Week 38 | ALICE_PHOS | PS Run for Beam request in Protons ... | Wednesday | 2023-09-20 | 14 | T9 | Scheduled | Main user
September | Week 39 | ALICE_ITS3 | PS Run September | Wednesday | 2023-09-27 | 7 | T10 | Scheduled | Main user
October | Week 40 | OREO | OREO | Wednesday | 2023-10-04 | 7 | T9 | Scheduled | Main user
October | Week 40 | ALICE_RICH | Study of SiPM response | Wednesday | 2023-10-04 | 14 | T10 | Scheduled | Main user
October | Week 40 | EIC_DRICH | EIC dRICH test beam at PS | Wednesday | 2023-10-04 | 14 | T10 | Scheduled | Parasitic user
October | Week 41 | ALICE_FOCAL | PS | Wednesday | 2023-10-11 | 7 | T9 | Scheduled | Main user
October | Week 42 | CHIMERA | EA-IRRAD ion run | Wednesday | 2023-10-18 | 12 | T8 | Scheduled | Main user
October | Week 42 | SHIP | SHiP-SBT | Wednesday | 2023-10-18 | 12 | T9 | Scheduled | Main user
October | Week 42 | ALICE_TIMING | Alice3 Timing run 2 | Wednesday | 2023-10-18 | 7 | T10 | Scheduled | Main user
October | Week 42 | ALICE_TOF | ALICE_TOF_fast_timing_2 | Wednesday | 2023-10-18 | 7 | T10 | Scheduled | Parasitic user
October | Week 43 | ALICE_ITS3 | PS Run October | Wednesday | 2023-10-25 | 5 | T10 | Scheduled | Main user
October | Week 43 | ALICE_TOF | ALICE_TOF_fast_timing_2 | Wednesday | 2023-10-25 | 5 | T10 | Scheduled | Parasitic user
October | Week 43 | CLOUD | CLOUD16 | Monday | 2023-10-30 | 35 | T11 | Scheduled | No beam (access only)