## Sheet
Changelog from _v330 until _v340, Status 20241003 00:00:00 (UTC)
Action | Run Id | Activiy | Last Changed | Changed Attribute | Previous Value | Latest Value
UPDATED | 148 | EIC_DRICH | 2024-09-11 16:42:32 (UTC) | Period | Protons 2024 | Protons 2024
|  |  |  | Week | 41 | 43
|  |  |  | Begin | 2024-10-09 | 2024-10-23
|  |  |  | End | 2024-10-16 | 2024-10-31
|  |  |  | Location | SPS[NA] / H6 / PPE156 / i | SPS[NA] / H6 / PPE156 / i
|  |  |  | Status | Scheduled | Scheduled
|  |  |  | Usage | Main user | Parasitic user
|  |  |  | Duration [Days] | 7 | 7
|  |  |  | Run Name | Run No. 1 for Activity ... | Run No. 1 for Activity ...
CREATED | 281 | ATLAS_AFP_TOF | 2024-09-12 12:13:29 (UTC) | Period |  | Protons 2024
|  |  |  | Week |  | 41
|  |  |  | Begin |  | 2024-08-07
|  |  |  | End |  | 2024-08-21
|  |  |  | Location |  | SPS[NA] / H6 / PPE156 / i
|  |  |  | Status |  | Withdrawn
|  |  |  | Usage |  | Main user
|  |  |  | Duration [Days] |  | 7
|  |  |  | Run Name |  | Run No. 1 for Activity ...
CREATED | 282 | ATLAS_AFP_TOF | 2024-09-12 12:16:49 (UTC) | Period |  | Protons 2024
|  |  |  | Week |  | 42
|  |  |  | Begin |  | 2024-09-04
|  |  |  | End |  | 2024-09-11
|  |  |  | Location |  | SPS[NA] / H6 / PPE156 / i
|  |  |  | Status |  | Withdrawn
|  |  |  | Usage |  | Parasitic user
|  |  |  | Duration [Days] |  | 7
|  |  |  | Run Name |  | Run No. 2 for Activity ...
UPDATED | 282 | ATLAS_AFP_TOF | 2024-09-12 12:52:52 (UTC) | Period | Protons 2024 | Protons 2024
|  |  |  | Week | 42 | 42
|  |  |  | Begin | 2024-09-04 | 2024-10-16
|  |  |  | End | 2024-09-11 | 2024-10-23
|  |  |  | Location | SPS[NA] / H6 / PPE156 / i | SPS[NA] / H6 / PPE156 / i
|  |  |  | Status | Withdrawn | Scheduled
|  |  |  | Usage | Parasitic user | Parasitic user
|  |  |  | Duration [Days] | 7 | 7
|  |  |  | Run Name | Run No. 2 for Activity ... | Run No. 2 for Activity ...
UPDATED | 281 | ATLAS_AFP_TOF | 2024-09-12 12:53:18 (UTC) | Period | Protons 2024 | Protons 2024
|  |  |  | Week | 41 | 41
|  |  |  | Begin | 2024-08-07 | 2024-10-09
|  |  |  | End | 2024-08-21 | 2024-10-16
|  |  |  | Location | SPS[NA] / H6 / PPE156 / i | SPS[NA] / H6 / PPE156 / i
|  |  |  | Status | Withdrawn | Scheduled
|  |  |  | Usage | Main user | Main user
|  |  |  | Duration [Days] | 7 | 7
|  |  |  | Run Name | Run No. 1 for Activity ... | Run No. 1 for Activity ...
CREATED | 283 | BI XBPF | 2024-09-24 11:37:39 (UTC) | Period |  | Protons 2024
|  |  |  | Week |  | 40
|  |  |  | Begin |  | 2024-09-11
|  |  |  | End |  | 2024-09-18
|  |  |  | Location |  | SPS[NA] / H8 / PPE138
|  |  |  | Status |  | Scheduled
|  |  |  | Usage |  | Main user
|  |  |  | Duration [Days] |  | 7
|  |  |  | Run Name |  | Run No. 1 for Activity ...
UPDATED | 283 | BI XBPF | 2024-09-24 11:41:13 (UTC) | Period | Protons 2024 | Protons 2024
|  |  |  | Week | 40 | 40
|  |  |  | Begin | 2024-09-11 | 2024-10-02
|  |  |  | End | 2024-09-18 | 2024-10-09
|  |  |  | Location | SPS[NA] / H8 / PPE138 | SPS[NA] / H8 / PPE138
|  |  |  | Status | Scheduled | Scheduled
|  |  |  | Usage | Main user | Main user
|  |  |  | Duration [Days] | 7 | 7
|  |  |  | Run Name | Run No. 1 for Activity ... | Run No. 1 for Activity ...
CREATED | 284 | ATLAS_TILECAL | 2024-09-27 12:25:38 (UTC) | Period |  | Protons 2024
|  |  |  | Week |  | 40
|  |  |  | Begin |  | 2024-09-18
|  |  |  | End |  | 2024-10-02
|  |  |  | Location |  | SPS[NA] / H8 / PPE158
|  |  |  | Status |  | Scheduled
|  |  |  | Usage |  | Parallel user
|  |  |  | Duration [Days] |  | 0
|  |  |  | Run Name |  | Run No. 2 for ATLAS TILECAL
UPDATED | 284 | ATLAS_TILECAL | 2024-09-27 12:26:02 (UTC) | Period | Protons 2024 | Protons 2024
|  |  |  | Week | 40 | 40
|  |  |  | Begin | 2024-09-18 | 2024-10-02
|  |  |  | End | 2024-10-02 | 2024-10-09
|  |  |  | Location | SPS[NA] / H8 / PPE158 | SPS[NA] / H8 / PPE158
|  |  |  | Status | Scheduled | Scheduled
|  |  |  | Usage | Parallel user | Parallel user
|  |  |  | Duration [Days] | 7 | 7
|  |  |  | Run Name | Run No. 2 for ATLAS TILECAL | Run No. 2 for ATLAS TILECAL
UPDATED | 200 | ALICE_FOCAL | 2024-10-02 07:56:32 (UTC) | Period | Protons 2024 | Protons 2024
|  |  |  | Week | 44 | 44
|  |  |  | Begin | 2024-10-30 | 2024-10-30
|  |  |  | End | 2024-11-06 | 2024-11-06
|  |  |  | Location | PS[EA]_T10 | PS[EA]_T10
|  |  |  | Status | Scheduled | Scheduled
|  |  |  | Usage | Parallel user | Main user
|  |  |  | Duration [Days] | 7 | 7
|  |  |  | Run Name | October Run "ALICE FOCAL" ... | October Run "ALICE FOCAL" ...
CREATED | 285 | NA61_SHINE | 2024-10-02 12:18:39 (UTC) | Period |  | Protons 2024
|  |  |  | Week |  | 42
|  |  |  | Begin |  | 2024-10-21
|  |  |  | End |  | 2024-10-24
|  |  |  | Location |  | SPS[NA] / H2 / PPE152 (H2A)
|  |  |  | Status |  | Draft
|  |  |  | Usage |  | Main user
|  |  |  | Duration [Days] |  | 0
|  |  |  | Run Name |  | pi+ + C for NA61 SHINE in ...
CREATED | 287 | NA61_SHINE | 2024-10-02 12:18:39 (UTC) | Period |  | Protons 2024
|  |  |  | Week |  | 43
|  |  |  | Begin |  | 2024-10-24
|  |  |  | End |  | 2024-10-27
|  |  |  | Location |  | SPS[NA] / H2 / PPE152 (H2A)
|  |  |  | Status |  | Draft
|  |  |  | Usage |  | Main user
|  |  |  | Duration [Days] |  | 0
|  |  |  | Run Name |  | Copy of pi- + C for NA61 ...
CREATED | 288 | NA61_SHINE | 2024-10-02 12:18:39 (UTC) | Period |  | Protons 2024
|  |  |  | Week |  | 43
|  |  |  | Begin |  | 2024-10-27
|  |  |  | End |  | 2024-11-01
|  |  |  | Location |  | SPS[NA] / H2 / PPE152 (H2A)
|  |  |  | Status |  | Draft
|  |  |  | Usage |  | Main user
|  |  |  | Duration [Days] |  | 0
|  |  |  | Run Name |  | Second PSD callibration run
UPDATED | 285 | NA61_SHINE | 2024-10-02 12:39:34 (UTC) | Period | Protons 2024 | Protons 2024
|  |  |  | Week | 42 | 42
|  |  |  | Begin | 2024-10-21 | 2024-10-21
|  |  |  | End | 2024-10-24 | 2024-10-24
|  |  |  | Location | SPS[NA] / H2 / PPE152 (H2A) | SPS[NA] / H2 / PPE152 (H2A)
|  |  |  | Status | Draft | Scheduled
|  |  |  | Usage | Main user | Main user
|  |  |  | Duration [Days] | 3 | 3
|  |  |  | Run Name | pi+ + C for NA61 SHINE in ... | pi+ + C for NA61 SHINE in ...
UPDATED | 287 | NA61_SHINE | 2024-10-02 12:40:18 (UTC) | Period | Protons 2024 | Protons 2024
|  |  |  | Week | 43 | 43
|  |  |  | Begin | 2024-10-24 | 2024-10-24
|  |  |  | End | 2024-10-27 | 2024-10-27
|  |  |  | Location | SPS[NA] / H2 / PPE152 (H2A) | SPS[NA] / H2 / PPE152 (H2A)
|  |  |  | Status | Draft | Scheduled
|  |  |  | Usage | Main user | Main user
|  |  |  | Duration [Days] | 3 | 3
|  |  |  | Run Name | Copy of pi- + C for NA61 ... | Copy of pi- + C for NA61 ...
UPDATED | 68 | NA61_SHINE | 2024-10-02 13:47:00 (UTC) | Period | Protons 2024 | Protons 2024
|  |  |  | Week | 42 | 42
|  |  |  | Begin | 2024-10-16 | 2024-10-16
|  |  |  | End | 2024-10-23 | 2024-10-21
|  |  |  | Location | SPS[NA] / H2 / PPE152 (H2A) | SPS[NA] / H2 / PPE152 (H2A)
|  |  |  | Status | Scheduled | Scheduled
|  |  |  | Usage | Main user | Main user
|  |  |  | Duration [Days] | 7 | 1
|  |  |  | Run Name | Run No. 3 for Activity ... | Run No. 3 for Activity ...
UPDATED | 288 | NA61_SHINE | 2024-10-02 13:48:57 (UTC) | Period | Protons 2024 | Protons 2024
|  |  |  | Week | 43 | 43
|  |  |  | Begin | 2024-10-27 | 2024-10-27
|  |  |  | End | 2024-11-01 | 2024-10-31
|  |  |  | Location | SPS[NA] / H2 / PPE152 (H2A) | SPS[NA] / H2 / PPE152 (H2A)
|  |  |  | Status | Draft | Scheduled
|  |  |  | Usage | Main user | Main user
|  |  |  | Duration [Days] | 4 | 4
|  |  |  | Run Name | Second PSD callibration run | Second PSD callibration run