## Sheet
Changelog from v340 until v400, Status 20241017 17:00:00 (UTC)
Action | Run Id | Activiy | Last Changed | Changed Attribute | Previous Value | Latest Value
UPDATED | 68 | NA61_SHINE | 2024-10-02 13:47:00 (UTC) | Period | Protons 2024 | Protons 2024
|  |  |  | Week | 42 | 42
|  |  |  | Begin | 2024-10-16 | 2024-10-16
|  |  |  | End | 2024-10-23 | 2024-10-21
|  |  |  | Location | SPS[NA] / H2 / PPE152 (H2A) | SPS[NA] / H2 / PPE152 (H2A)
|  |  |  | Status | Scheduled | Scheduled
|  |  |  | Usage | Main user | Main user
|  |  |  | Duration [Days] | 7 | 1
|  |  |  | Run Name | Run No. 3 for Activity ... | Run No. 3 for Activity ...
UPDATED | 288 | NA61_SHINE | 2024-10-02 13:48:57 (UTC) | Period | Protons 2024 | Protons 2024
|  |  |  | Week | 43 | 43
|  |  |  | Begin | 2024-10-27 | 2024-10-27
|  |  |  | End | 2024-11-01 | 2024-10-31
|  |  |  | Location | SPS[NA] / H2 / PPE152 (H2A) | SPS[NA] / H2 / PPE152 (H2A)
|  |  |  | Status | Scheduled | Scheduled
|  |  |  | Usage | Main user | Main user
|  |  |  | Duration [Days] | 5 | 5
|  |  |  | Run Name | Second PSD callibration run | Second PSD callibration run
CREATED | 289 | ATLAS_HGTD | 2024-10-04 09:34:13 (UTC) | Period |  | Protons 2024
|  |  |  | Week |  | 41
|  |  |  | Begin |  | 2024-09-18
|  |  |  | End |  | 2024-09-25
|  |  |  | Location |  | SPS[NA] / H6 / PPE146 / d (ACONITE)
|  |  |  | Status |  | Scheduled
|  |  |  | Usage |  | Parallel user
|  |  |  | Duration [Days] |  | 7
|  |  |  | Run Name |  | Run No. 3 for Activity ...
UPDATED | 289 | ATLAS_HGTD | 2024-10-04 09:34:57 (UTC) | Period | Protons 2024 | Protons 2024
|  |  |  | Week | 41 | 41
|  |  |  | Begin | 2024-09-18 | 2024-10-09
|  |  |  | End | 2024-09-25 | 2024-10-16
|  |  |  | Location | SPS[NA] / H6 / PPE146 / d (ACONITE) | SPS[NA] / H6 / PPE146 / d (ACONITE)
|  |  |  | Status | Scheduled | Scheduled
|  |  |  | Usage | Parallel user | Parallel user
|  |  |  | Duration [Days] | 7 | 7
|  |  |  | Run Name | Run No. 3 for Activity ... | Run No. 3 for Activity ...
CREATED | 290 | PAX | 2024-10-08 10:22:26 (UTC) | Period |  | AD/ELENA 2024
|  |  |  | Week |  | 42
|  |  |  | Begin |  | 2024-10-10
|  |  |  | End |  | 2024-10-17
|  |  |  | Location |  | AD-ELENA / TELMAX
|  |  |  | Status |  | Draft
|  |  |  | Usage |  | Main user
|  |  |  | Duration [Days] |  | 7
|  |  |  | Run Name |  | PAX-First Test
UPDATED | 290 | PAX | 2024-10-08 10:24:25 (UTC) | Period | AD/ELENA 2024 | AD/ELENA 2024
|  |  |  | Week | 42 | 42
|  |  |  | Begin | 2024-10-10 | 2024-10-16
|  |  |  | End | 2024-10-17 | 2024-10-23
|  |  |  | Location | AD-ELENA / TELMAX | AD-ELENA / TELMAX
|  |  |  | Status | Draft | Scheduled
|  |  |  | Usage | Main user | Main user
|  |  |  | Duration [Days] | 7 | 7
|  |  |  | Run Name | PAX-First Test | PAX-First Test
UPDATED | 56 | LHCB | 2024-10-16 12:23:52 (UTC) | Period | Protons 2024 | Protons 2024
|  |  |  | Week | 42 | 43
|  |  |  | Begin | 2024-10-16 | 2024-10-23
|  |  |  | End | 2024-10-31 | 2024-10-31
|  |  |  | Location | SPS[NA] / H8 / PPE138 | SPS[NA] / H8 / PPE138
|  |  |  | Status | Scheduled | Scheduled
|  |  |  | Usage | Main user | Main user
|  |  |  | Duration [Days] | 15 | 15
|  |  |  | Run Name | Run No. 3 for Activity "LHCb" | Run No. 3 for Activity "LHCb"
UPDATED | 115 | 4DPHOTON | 2024-10-16 12:28:40 (UTC) | Period | Protons 2024 | Protons 2024
|  |  |  | Week | 40 | 43
|  |  |  | Begin | 2024-10-02 | 2024-10-23
|  |  |  | End | 2024-10-09 | 2024-10-31
|  |  |  | Location | SPS[NA] / H8 / PPE138 | SPS[NA] / H8 / PPE168
|  |  |  | Status | Withdrawn | Scheduled
|  |  |  | Usage | Main user | Parallel user
|  |  |  | Duration [Days] | 7 | 1
|  |  |  | Run Name | Run No. 1 for Activity ... | Run No. 1 for Activity ...
UPDATED | 48 | LHCB | 2024-10-16 12:34:47 (UTC) | Period | Protons 2024 | Protons 2024
|  |  |  | Week | 42 | 43
|  |  |  | Begin | 2024-10-16 | 2024-10-23
|  |  |  | End | 2024-10-31 | 2024-10-30
|  |  |  | Location | SPS[NA] / H8 / PPE168 | SPS[NA] / H8 / PPE168
|  |  |  | Status | Scheduled | Withdrawn
|  |  |  | Usage | Parallel user | Parallel user
|  |  |  | Duration [Days] | 15 | 15
|  |  |  | Run Name | Muons Run SPS - Parallel ... | Muons Run SPS - Parallel ...
UPDATED | 144 | UA9 | 2024-10-16 12:38:12 (UTC) | Period | Protons 2024 | Protons 2024
|  |  |  | Week | 42 | 42
|  |  |  | Begin | 2024-10-16 | 2024-10-16
|  |  |  | End | 2024-10-23 | 2024-10-23
|  |  |  | Location | SPS[NA] / H8 / PPE128 | SPS[NA] / H8 / PPE128
|  |  |  | Status | Scheduled | Scheduled
|  |  |  | Usage | Parallel user | Main user
|  |  |  | Duration [Days] | 7 | 7
|  |  |  | Run Name | UA9 Run 2 | UA9 Run 2
UPDATED | 223 | PAN | 2024-10-17 10:11:32 (UTC) | Period | Lead Ions 2024 | Lead Ions 2024
|  |  |  | Week | 47 | 44
|  |  |  | Begin | 2024-11-25 | 2024-11-04
|  |  |  | End | 2024-12-02 | 2024-11-11
|  |  |  | Location | SPS[NA] / H8 / PPE138 | SPS[NA] / H8 / PPE138
|  |  |  | Status | Draft | Draft
|  |  |  | Usage | Parallel user | Parasitic user
|  |  |  | Duration [Days] | 7 | 7
|  |  |  | Run Name | Run No. 1 for Activity ... | Run No. 1 for Activity ...
UPDATED | 64 | CMS_ECAL | 2024-10-17 11:30:29 (UTC) | Period | Protons 2024 | Protons 2024
|  |  |  | Week | 42 | 42
|  |  |  | Begin | 2024-10-16 | 2024-10-16
|  |  |  | End | 2024-10-31 | 2024-10-25
|  |  |  | Location | SPS[NA] / H4 / PPE164 (H4D) | SPS[NA] / H4 / PPE164 (H4D)
|  |  |  | Status | Scheduled | Scheduled
|  |  |  | Usage | Main user | Main user
|  |  |  | Duration [Days] | 15 | 15
|  |  |  | Run Name | Run No. 1 for Activity ... | Run No. 1 for Activity ...