## Sheet1
North Area Schedule v1.2.0 :: ENH1 All Beamlines H2, H4, H6 & H8 :: Status 2023-05-08 13:30 UTC
Schedule Run
The scheduled runs presented in this file result from applying the following filters:
Beamlines |  | Only runs which have been scheduled in either of the beamlines "H2, H4, H6, H8" are included below.
Associated Month | Associated Week | Activity | Run name | Start Weekday | Start Date | Duration [days] | Location | Status | Usage
March | Week 12 | MADMAX | MADMAX | Tuesday | 2023-03-28 | 24 | PPE158 | Scheduled | No beam (access only)
April | Week 16 | CALICE_SCW_AHCAL | CALICE ScW-ECAL + AHCAL at SPS(H2/H4) | Monday | 2023-04-24 | 16 | PPE172 | Scheduled | Main user
April | Week 16 | RD51 | RD51 - Period 1 | Monday | 2023-04-24 | 16 | PPE134 | Scheduled | Parallel user
April | Week 16 | STRAW_TRACKER_RD | Run in parallel to RD51 #1 | Monday | 2023-04-24 | 16 | PPE134 | Scheduled | Parasitic user
April | Week 16 | GIF++ | Muon Run 1 | Monday | 2023-04-24 | 16 | PPE154 | Scheduled | Main user
April | Week 16 | ATLAS_ITK_PIXEL | DAQ development, re-commissioning, ... | Monday | 2023-04-24 | 16 | PPE146 / d | Scheduled | Main user
April | Week 16 | LHCB | Run 1 (H8.A) | Monday | 2023-04-24 | 16 | PPE138 | Scheduled | Main user
May | Week 18 | RD42 | First run (earlier) | Wednesday | 2023-05-03 | 7 | PPE146 / g | Scheduled | Parallel user
May | Week 18 | CMS_PIXEL | CMS Pixels 2023 May Run | Wednesday | 2023-05-03 | 7 | PPE156 / h | Scheduled | Parallel user
May | Week 19 | CMS_HF | HF Q-Wall 2023 | Wednesday | 2023-05-10 | 7 | PPE172 | Scheduled | Main user
May | Week 19 | NA64e | NA64e | Wednesday | 2023-05-10 | 56 | PPE144 | Scheduled | Main user
May | Week 19 | ATLAS_ITK_PIXEL | DAQ development, re-commissioning, ... | Wednesday | 2023-05-10 | 14 | PPE146 / d | Scheduled | Parasitic user
May | Week 19 | CERF | CERF run | Wednesday | 2023-05-10 | 7 | PPE126 | Scheduled | Main user
May | Week 19 | CMS_MTD | BTL May Run | Wednesday | 2023-05-10 | 14 | PPE158 | Scheduled | Main user
May | Week 19 | STRAW_TRACKER_RD | parasitic H8 beam dump #1 | Wednesday | 2023-05-10 | 14 | DUMP[H8] | Scheduled | Parasitic user
May | Week 20 | ALICE_FOCAL | SPS | Wednesday | 2023-05-17 | 7 | PPE172 | Scheduled | Main user
May | Week 20 | ALICE_ITS3 | SPS Run #3 | Wednesday | 2023-05-17 | 7 | PPE146 / f | Scheduled | Parallel user
May | Week 20 | ATLAS_MALTA | Run no. 0 for Beam request in ... | Wednesday | 2023-05-17 | 7 | PPE146 / g | Scheduled | Parasitic user
May | Week 20 | EP_PIXEL | run 1 | Wednesday | 2023-05-17 | 7 | PPE156 / j | Scheduled | Main user
May | Week 20 | TOTEM_PPS | June | Wednesday | 2023-05-17 | 7 | PPE168 | Scheduled | Parallel user
May | Week 21 | RADICAL | Run no. 0 for Beam request in ... | Wednesday | 2023-05-24 | 7 | PPE172 | Scheduled | Main user
May | Week 21 | ATLAS_HGTD | LGAD testing | Wednesday | 2023-05-24 | 14 | PPE146 / d | Scheduled | Parallel user
May | Week 21 | ATLAS_AFP_TOF | AFP-ToF PicoTDC testing and integration | Wednesday | 2023-05-24 | 7 | PPE156 / i | Scheduled | Main user
May | Week 21 | SND | SND@LHC HCAL/Muon | Wednesday | 2023-05-24 | 7 | PPE168 | Scheduled | No beam (access only)
May | Week 22 | MUONE_ECAL | MUONE ECAL Calibration at high energy | Wednesday | 2023-05-31 | 10 | PPE172 | Scheduled | Main user
May | Week 22 | ATLAS_BCM_PRIME | ATLAS BCM' | Wednesday | 2023-05-31 | 7 | PPE146 / g | Scheduled | Main user
May | Week 22 | ATLAS_AFP_TOF | AFP-ToF PicoTDC testing and integration | Wednesday | 2023-05-31 | 7 | PPE156 / i | Scheduled | Parallel user
May | Week 22 | SND | SND@LHC HCAL/Muon | Wednesday | 2023-05-31 | 7 | PPE168 | Scheduled | Main user
June | Week 23 | ALICE_ITS3 | SPS Run | Wednesday | 2023-06-07 | 7 | PPE146 / f | Scheduled | Main user
June | Week 23 | EP_PIXEL | run 2 | Wednesday | 2023-06-07 | 7 | PPE156 / j | Scheduled | Parallel user
June | Week 23 | GALORE | Run no. 0 for Beam request in ... | Wednesday | 2023-06-07 | 7 | PPE128 | Scheduled | Parallel user
June | Week 23 | CMS_MTD | BTL May Run | Wednesday | 2023-06-07 | 7 | PPE158 | Scheduled | Parasitic user
June | Week 23 | PROTOV | ProToV 2023 | Wednesday | 2023-06-07 | 7 | PPE168 | Scheduled | Main user
June | Week 23 | EP_FTS | 2023 run | Saturday | 2023-06-10 | 4 | PPE172 | Scheduled | Main user
June | Week 24 | ATLAS_ZDC | ATLAS ZDC-RPD test beam | Wednesday | 2023-06-14 | 7 | PPE172 | Scheduled | Main user
June | Week 24 | ATLAS_ITK_PIXEL | Angle studies in ACONITE | Wednesday | 2023-06-14 | 7 | PPE146 / d | Scheduled | Main user
June | Week 24 | AIDAINNOVA_WP6 | AIDAInnova_4D | Wednesday | 2023-06-14 | 14 | PPE156 / h | Scheduled | Parallel user
June | Week 24 | STI | STI run#1 | Wednesday | 2023-06-14 | 7 | PPE128 | Scheduled | Parallel user
June | Week 24 | LHCB | Run 2 (H8.A) | Wednesday | 2023-06-14 | 7 | PPE138 | Scheduled | Parallel user
June | Week 24 | TOTEM_PPS | July | Wednesday | 2023-06-14 | 7 | PPE168 | Scheduled | Main user
June | Week 24 | LHCB | Muon Run 1 (H8.C) | Wednesday | 2023-06-14 | 14 | PPE168 | Scheduled | Parallel user
June | Week 25 | LHCB_ECAL | Run 1 | Wednesday | 2023-06-21 | 14 | PPE172 | Scheduled | Main user
June | Week 25 | ATLAS_ITK_PIXEL | Testing of early pre-production ... | Wednesday | 2023-06-21 | 7 | PPE146 / d | Scheduled | Main user
June | Week 25 | UA9 | UA9 Run 1 | Wednesday | 2023-06-21 | 7 | PPE128 | Scheduled | Parallel user
June | Week 25 | LHCB | Run 2 (H8.A) | Wednesday | 2023-06-21 | 7 | PPE138 | Scheduled | Main user
June | Week 25 | STRAW_TRACKER_RD | parasitic H8 beam dump #2 | Wednesday | 2023-06-21 | 14 | DUMP[H8] | Scheduled | Parasitic user
June | Week 26 | ATLAS_ITK_PIXEL | Angle studies in ACONITE | Wednesday | 2023-06-28 | 7 | PPE146 / d | Scheduled | Parallel user
June | Week 26 | CMS_MTD | ETL August Run | Wednesday | 2023-06-28 | 7 | PPE156 / h | Scheduled | Main user
June | Week 26 | EXFLU | EXFLU SEB 1 | Wednesday | 2023-06-28 | 14 | PPE156 | Scheduled | Parasitic user
June | Week 26 | IDEA_DRC | Test of dual-readout calorimeter ... | Wednesday | 2023-06-28 | 7 | PPE168 | Scheduled | Main user
July | Week 27 | NA61_SHINE | K+ 60 run | Wednesday | 2023-07-05 | 28 | PPE152 | Scheduled | Main user
July | Week 27 | RD51 | RD51 - Period 2 | Wednesday | 2023-07-05 | 14 | PPE134 | Scheduled | Main user
July | Week 27 | MINICACTUS | Run in parallel to RD51 | Wednesday | 2023-07-05 | 7 | PPE134 | Scheduled | Parasitic user
July | Week 27 | STRAW_TRACKER_RD | Run in parallel to RD51 #2 | Wednesday | 2023-07-05 | 14 | PPE134 | Scheduled | Parasitic user
July | Week 27 | GIF++ | Muon Run 2 | Wednesday | 2023-07-05 | 14 | PPE154 | Scheduled | Parallel user
July | Week 27 | MONOLITH | Parasitic2022 | Wednesday | 2023-07-05 | 7 | PPE156 / i | Scheduled | Parasitic user
July | Week 27 | EP_PIXEL | run 3 | Wednesday | 2023-07-05 | 7 | PPE156 / j | Scheduled | Main user
July | Week 27 | ATLAS_TILECAL | July Run | Wednesday | 2023-07-05 | 14 | PPE158 | Scheduled | Main user
July | Week 28 | ATLAS_HGTD | Module testing | Wednesday | 2023-07-12 | 14 | PPE146 / d | Scheduled | Parallel user
July | Week 28 | CMS_PIXEL | CMS Pixels 2023 July Run | Wednesday | 2023-07-12 | 14 | PPE156 / h | Scheduled | Main user
July | Week 29 | CMS_ECAL | CMS ECAL 2023 | Wednesday | 2023-07-19 | 14 | PPE164 | Scheduled | Main user
July | Week 29 | MPGD_TRD | MPGD-TRD-EIC | Wednesday | 2023-07-19 | 7 | PPE138 | Scheduled | Main user
July | Week 29 | QFIB | Main QFib | Wednesday | 2023-07-19 | 7 | PPE138 | Scheduled (cond.) | Parasitic user
July | Week 30 | ALICE_ITS3 | SPS Run #2 | Wednesday | 2023-07-26 | 7 | PPE146 / f | Scheduled | Parallel user
July | Week 30 | MONOLITH | Parasitic2022 | Wednesday | 2023-07-26 | 7 | PPE156 / i | Scheduled | Parasitic user
July | Week 30 | EP_PIXEL | run 4 | Wednesday | 2023-07-26 | 7 | PPE156 / j | Scheduled | Main user
July | Week 30 | POKER | POKERINO | Wednesday | 2023-07-26 | 7 | PPE158 | Scheduled | Main user
August | Week 31 | NA61_SHINE | proton 120 run | Wednesday | 2023-08-02 | 14 | PPE152 | Scheduled | Main user
August | Week 31 | CMS_HGCAL | HGCal July Run | Wednesday | 2023-08-02 | 7 | PPE134 | Scheduled | Main user
August | Week 31 | ATLAS_ITK_PIXEL | Testing of irradiated modules | Wednesday | 2023-08-02 | 7 | PPE146 / d | Scheduled | Main user
August | Week 31 | QFIB | Qfib parasitic | Wednesday | 2023-08-02 | 7 | PPE138 | Scheduled | Main user
August | Week 31 | SND | SND@LHC HCAL/Muon | Wednesday | 2023-08-02 | 7 | PPE168 | Scheduled | Parasitic user
August | Week 32 | CMS_ZDC_EM | CMS ZDC EM Calibration 2023 | Wednesday | 2023-08-09 | 7 | PPE134 | Scheduled | Main user
August | Week 32 | RD42 | Parasitic run | Wednesday | 2023-08-09 | 7 | PPE146 / a | Scheduled (prov.) | Parasitic user
August | Week 32 | ATLAS_ITK_STRIP | Run no. 0 for Beam request in ... | Wednesday | 2023-08-09 | 7 | PPE146 / d | Scheduled | Main user
August | Week 32 | MEDIPIX | Medipix (SPS) | Wednesday | 2023-08-09 | 7 | PPE156 | Scheduled | Parallel user
August | Week 32 | SND | SND@LHC HCAL/Muon | Wednesday | 2023-08-09 | 7 | PPE168 | Scheduled (cond.) | Main user
August | Week 32 | STRAW_TRACKER_RD | parasitic H8 beam dump #3 | Wednesday | 2023-08-09 | 14 | DUMP[H8] | Scheduled | Parasitic user
August | Week 33 | HIKE_SAC | HIKE SAC 2023 | Wednesday | 2023-08-16 | 7 | PPE172 | Scheduled | Main user
August | Week 33 | FASER_NU | FASERnu | Wednesday | 2023-08-16 | 7 | PPE134 | Scheduled | Main user
August | Week 33 | EIC_DRICH | EIC dRICH test beam at SPS | Wednesday | 2023-08-16 | 7 | PPE146 / f | Scheduled | Main user
August | Week 33 | RE1_AMS_L0 | Spatial resolution measurement | Wednesday | 2023-08-16 | 7 | PPE138 | Scheduled | Main user
August | Week 34 | LHCB_ECAL | Run 2 | Wednesday | 2023-08-23 | 14 | PPE172 | Scheduled | Main user
August | Week 34 | RD51 | RD51 - Period 3 | Wednesday | 2023-08-23 | 14 | PPE134 | Scheduled | Parallel user
August | Week 34 | STRAW_TRACKER_RD | Run in parallel to RD51 #3 | Wednesday | 2023-08-23 | 14 | PPE134 | Scheduled | Parasitic user
August | Week 34 | GIF++ | Muon Run 3 | Wednesday | 2023-08-23 | 14 | PPE154 | Scheduled | Main user
August | Week 34 | MONOLITH | Run2022 | Wednesday | 2023-08-23 | 7 | PPE156 / i | Scheduled | Main user
August | Week 34 | EP_PIXEL | run 5 | Wednesday | 2023-08-23 | 7 | PPE156 / j | Scheduled | Parallel user
August | Week 34 | SELDOM | Run 2 | Wednesday | 2023-08-23 | 7 | PPE128 | Scheduled | Parallel user
August | Week 35 | RD42 | Second run | Wednesday | 2023-08-30 | 7 | PPE146 / a | Scheduled | Parallel user
August | Week 35 | ATLAS_HGTD | Module testing 2 | Wednesday | 2023-08-30 | 14 | PPE146 / d | Scheduled | Main user
August | Week 35 | AIDAINNOVA_WP6 | AIDAInnova_4D | Wednesday | 2023-08-30 | 7 | PPE156 / h | Scheduled | Parallel user
August | Week 35 | ATLAS_TILECAL | September run | Wednesday | 2023-08-30 | 14 | PPE158 | Scheduled | Main user
September | Week 36 | CMS_HGCAL | HGCal September Run | Wednesday | 2023-09-06 | 14 | PPE172 | Scheduled (cond.) | Main user
September | Week 36 | PLACE_HOLDER | Placeholder Run | Wednesday | 2023-09-06 | 7 | H4 | Scheduled (cond.) | Main user
September | Week 36 | CMS_PIXEL | CMS Pixels 2023 September Run | Wednesday | 2023-09-06 | 7 | PPE156 / h | Scheduled | Parallel user
September | Week 36 | PAN | High energy protons | Wednesday | 2023-09-06 | 7 | PPE156 | Scheduled | Parasitic user
September | Week 37 | NA65 | Physics | Wednesday | 2023-09-13 | 14 | PPE134 | Scheduled (cond.) | Main user
September | Week 37 | PICSEL | PICSEL - MIMOSIS | Wednesday | 2023-09-13 | 7 | PPE146 / c | Scheduled | Parallel user
September | Week 37 | ATLAS_ITK_PIXEL | Testing of multiple pre-production ... | Wednesday | 2023-09-13 | 14 | PPE146 / d | Scheduled | Main user
September | Week 37 | ATLAS_AFP_TOF | AFP-ToF R&D and backup equipment test | Wednesday | 2023-09-13 | 14 | PPE156 / i | Scheduled | Parasitic user
September | Week 37 | UA9 | UA9 Run 2 | Wednesday | 2023-09-13 | 7 | PPE128 | Scheduled | Main user
September | Week 37 | LHCB | Run 3 (H8.A) | Wednesday | 2023-09-13 | 14 | PPE138 | Scheduled | Parallel user
September | Week 37 | CMS_MTD | BTL September Run | Wednesday | 2023-09-13 | 7 | PPE158 | Scheduled | Parallel user
September | Week 37 | TOTEM_PPS | September | Wednesday | 2023-09-13 | 7 | PPE168 | Scheduled | Parallel user
September | Week 37 | LHCB | Muon Run 2 (H8.C) | Wednesday | 2023-09-13 | 14 | PPE168 | Scheduled | Parallel user
September | Week 38 | NA61_SHINE | hadrons PSD | Wednesday | 2023-09-20 | 7 | PPE152 | Scheduled (cond.) | Main user
September | Week 38 | ATLAS_BCM_PRIME | ATLAS BCM' | Wednesday | 2023-09-20 | 7 | PPE146 / g | Scheduled | Parallel user
September | Week 38 | CMS_MTD | ETL October Run | Wednesday | 2023-09-20 | 7 | PPE156 / h | Scheduled | Parallel user
September | Week 38 | STI | STI run#2 | Wednesday | 2023-09-20 | 7 | PPE128 | Scheduled | Parallel user
September | Week 38 | CMS_MTD | BTL September Run | Wednesday | 2023-09-20 | 7 | PPE158 | Scheduled | Main user
September | Week 39 | NA61_SHINE | Pb 150 run | Monday | 2023-10-02 | 28 | PPE152 | Scheduled | Main user
September | Week 39 | PAN | Fragmented ions run | Monday | 2023-10-02 | 7 | PPE134 | Scheduled | Main user
September | Week 39 | VLAST | VLAST ion run | Monday | 2023-10-02 | 7 | PPE138 | Scheduled | Main user
October | Week 40 | HERD | HERD SPS ion run | Monday | 2023-10-09 | 7 | PPE134 | Scheduled | Main user
October | Week 40 | NA60+ | NA60+ detector and beam optics tests | Monday | 2023-10-09 | 10 | PPE138 | Scheduled | Main user
October | Week 41 | MEDIPIX | Medipix | Monday | 2023-10-16 | 7 | PPE134 | Scheduled | Main user
October | Week 42 | R2E | R2E irradiation | Thursday | 2023-10-19 | 6 | PPE138 | Scheduled | Main user
October | Week 42 | RE1_AMS_L0 | Charge measurement | Monday | 2023-10-23 | 7 | PPE134 | Scheduled | Main user
October | Week 43 | RE7_GAMMA_MEV | Run no. 0 for Beam request in Ions ... | Wednesday | 2023-10-25 | 5 | PPE138 | Scheduled | Main user