## Sheet1
North Area Schedule v1.2.0 :: Beamline H8 :: Status 2023-05-08 13:30 UTC
Schedule Run
The scheduled runs presented in this file result from applying the following filters:
Beamlines |  | Only runs which have been scheduled in either of the beamlines "H8" are included below.
Associated Month | Associated Week | Activity | Run name | Start Weekday | Start Date | Duration [days] | Location | Status | Usage
March | Week 12 | MADMAX | MADMAX | Tuesday | 2023-03-28 | 24 | PPE158 | Scheduled | No beam (access only)
April | Week 16 | LHCB | Run 1 (H8.A) | Monday | 2023-04-24 | 16 | PPE138 | Scheduled | Main user
May | Week 19 | CMS_MTD | BTL May Run | Wednesday | 2023-05-10 | 14 | PPE158 | Scheduled | Main user
May | Week 19 | STRAW_TRACKER_RD | parasitic H8 beam dump #1 | Wednesday | 2023-05-10 | 14 | DUMP[H8] | Scheduled | Parasitic user
May | Week 20 | TOTEM_PPS | June | Wednesday | 2023-05-17 | 7 | PPE168 | Scheduled | Parallel user
May | Week 21 | SND | SND@LHC HCAL/Muon | Wednesday | 2023-05-24 | 7 | PPE168 | Scheduled | No beam (access only)
May | Week 22 | SND | SND@LHC HCAL/Muon | Wednesday | 2023-05-31 | 7 | PPE168 | Scheduled | Main user
June | Week 23 | GALORE | Run no. 0 for Beam request in ... | Wednesday | 2023-06-07 | 7 | PPE128 | Scheduled | Parallel user
June | Week 23 | CMS_MTD | BTL May Run | Wednesday | 2023-06-07 | 7 | PPE158 | Scheduled | Parasitic user
June | Week 23 | PROTOV | ProToV 2023 | Wednesday | 2023-06-07 | 7 | PPE168 | Scheduled | Main user
June | Week 24 | STI | STI run#1 | Wednesday | 2023-06-14 | 7 | PPE128 | Scheduled | Parallel user
June | Week 24 | LHCB | Run 2 (H8.A) | Wednesday | 2023-06-14 | 7 | PPE138 | Scheduled | Parallel user
June | Week 24 | TOTEM_PPS | July | Wednesday | 2023-06-14 | 7 | PPE168 | Scheduled | Main user
June | Week 24 | LHCB | Muon Run 1 (H8.C) | Wednesday | 2023-06-14 | 14 | PPE168 | Scheduled | Parallel user
June | Week 25 | UA9 | UA9 Run 1 | Wednesday | 2023-06-21 | 7 | PPE128 | Scheduled | Parallel user
June | Week 25 | LHCB | Run 2 (H8.A) | Wednesday | 2023-06-21 | 7 | PPE138 | Scheduled | Main user
June | Week 25 | STRAW_TRACKER_RD | parasitic H8 beam dump #2 | Wednesday | 2023-06-21 | 14 | DUMP[H8] | Scheduled | Parasitic user
June | Week 26 | IDEA_DRC | Test of dual-readout calorimeter ... | Wednesday | 2023-06-28 | 7 | PPE168 | Scheduled | Main user
July | Week 27 | ATLAS_TILECAL | July Run | Wednesday | 2023-07-05 | 14 | PPE158 | Scheduled | Main user
July | Week 29 | MPGD_TRD | MPGD-TRD-EIC | Wednesday | 2023-07-19 | 7 | PPE138 | Scheduled | Main user
July | Week 29 | QFIB | Main QFib | Wednesday | 2023-07-19 | 7 | PPE138 | Scheduled (cond.) | Parasitic user
July | Week 30 | POKER | POKERINO | Wednesday | 2023-07-26 | 7 | PPE158 | Scheduled | Main user
August | Week 31 | QFIB | Qfib parasitic | Wednesday | 2023-08-02 | 7 | PPE138 | Scheduled | Main user
August | Week 31 | SND | SND@LHC HCAL/Muon | Wednesday | 2023-08-02 | 7 | PPE168 | Scheduled | Parasitic user
August | Week 32 | SND | SND@LHC HCAL/Muon | Wednesday | 2023-08-09 | 7 | PPE168 | Scheduled (cond.) | Main user
August | Week 32 | STRAW_TRACKER_RD | parasitic H8 beam dump #3 | Wednesday | 2023-08-09 | 14 | DUMP[H8] | Scheduled | Parasitic user
August | Week 33 | RE1_AMS_L0 | Spatial resolution measurement | Wednesday | 2023-08-16 | 7 | PPE138 | Scheduled | Main user
August | Week 34 | SELDOM | Run 2 | Wednesday | 2023-08-23 | 7 | PPE128 | Scheduled | Parallel user
August | Week 35 | ATLAS_TILECAL | September run | Wednesday | 2023-08-30 | 14 | PPE158 | Scheduled | Main user
September | Week 37 | UA9 | UA9 Run 2 | Wednesday | 2023-09-13 | 7 | PPE128 | Scheduled | Main user
September | Week 37 | LHCB | Run 3 (H8.A) | Wednesday | 2023-09-13 | 14 | PPE138 | Scheduled | Parallel user
September | Week 37 | CMS_MTD | BTL September Run | Wednesday | 2023-09-13 | 7 | PPE158 | Scheduled | Parallel user
September | Week 37 | TOTEM_PPS | September | Wednesday | 2023-09-13 | 7 | PPE168 | Scheduled | Parallel user
September | Week 37 | LHCB | Muon Run 2 (H8.C) | Wednesday | 2023-09-13 | 14 | PPE168 | Scheduled | Parallel user
September | Week 38 | STI | STI run#2 | Wednesday | 2023-09-20 | 7 | PPE128 | Scheduled | Parallel user
September | Week 38 | CMS_MTD | BTL September Run | Wednesday | 2023-09-20 | 7 | PPE158 | Scheduled | Main user
September | Week 39 | VLAST | VLAST ion run | Monday | 2023-10-02 | 7 | PPE138 | Scheduled | Main user
October | Week 40 | NA60+ | NA60+ detector and beam optics tests | Monday | 2023-10-09 | 10 | PPE138 | Scheduled | Main user
October | Week 42 | R2E | R2E irradiation | Thursday | 2023-10-19 | 6 | PPE138 | Scheduled | Main user
October | Week 43 | RE7_GAMMA_MEV | Run no. 0 for Beam request in Ions ... | Wednesday | 2023-10-25 | 5 | PPE138 | Scheduled | Main user