## Sheet1
North Area Schedule v1.4.0 :: Beamlines H6 :: Status 2023-06-16 19:00 (UTC)
Schedule Run
The scheduled runs presented in this file result from applying the following filters:
Beamlines |  | Only runs which have been scheduled in either of the beamlines "H6" are included below.
Associated Month | Associated Week | Activity | Run name | Start Weekday | Start Date | Duration [days] | Location | Status | Usage
April | Week 16 | ATLAS_ITK_PIXEL | DAQ development, re-commissioning, ... | Monday | 2023-04-24 | 16 | PPE146 / d | Scheduled | Main user
May | Week 18 | RD42 | First run (earlier) | Wednesday | 2023-05-03 | 7 | PPE146 / g | Scheduled | Parallel user
May | Week 18 | CMS_PIXEL | CMS Pixels 2023 May Run | Wednesday | 2023-05-03 | 7 | PPE156 / h | Scheduled | Parallel user
May | Week 19 | ATLAS_ITK_PIXEL | DAQ development, re-commissioning, ... | Wednesday | 2023-05-10 | 14 | PPE146 / d | Scheduled | Parasitic user
May | Week 19 | CERF | CERF run | Wednesday | 2023-05-10 | 7 | PPE126 | Scheduled | Main user
May | Week 20 | ALICE_ITS3 | SPS Run #3 | Wednesday | 2023-05-17 | 7 | PPE146 / f | Scheduled | Parallel user
May | Week 20 | ATLAS_MALTA | Run no. 0 for Beam request in ... | Wednesday | 2023-05-17 | 7 | PPE146 / g | Scheduled | Parasitic user
May | Week 20 | EP_PIXEL | run 1 | Wednesday | 2023-05-17 | 7 | PPE156 / j | Scheduled | Main user
May | Week 21 | ATLAS_HGTD | LGAD testing | Wednesday | 2023-05-24 | 14 | PPE146 / d | Scheduled | Parallel user
May | Week 21 | ATLAS_AFP_TOF | AFP-ToF PicoTDC testing and integration | Wednesday | 2023-05-24 | 7 | PPE156 / i | Scheduled | Main user
May | Week 22 | ATLAS_BCM_PRIME | ATLAS BCM' | Wednesday | 2023-05-31 | 7 | PPE146 / g | Scheduled | Main user
May | Week 22 | ATLAS_AFP_TOF | AFP-ToF PicoTDC testing and integration | Wednesday | 2023-05-31 | 7 | PPE156 / i | Scheduled | Parallel user
June | Week 23 | ALICE_ITS3 | SPS Run | Wednesday | 2023-06-07 | 7 | PPE146 / f | Scheduled | Main user
June | Week 23 | EP_PIXEL | run 2 | Wednesday | 2023-06-07 | 7 | PPE156 / j | Scheduled | Parallel user
June | Week 24 | ATLAS_ITK_PIXEL | Angle studies in ACONITE | Wednesday | 2023-06-14 | 7 | PPE146 / d | Scheduled | Main user
June | Week 24 | AIDAINNOVA_WP6 | AIDAInnova_4D | Wednesday | 2023-06-14 | 14 | PPE156 / h | Scheduled | Parallel user
June | Week 25 | ATLAS_ITK_PIXEL | Testing of early pre-production ... | Wednesday | 2023-06-21 | 7 | PPE146 / d | Scheduled | Main user
June | Week 26 | ATLAS_ITK_PIXEL | Angle studies in ACONITE | Wednesday | 2023-06-28 | 7 | PPE146 / d | Scheduled | Parallel user
June | Week 26 | CMS_MTD | ETL August Run | Wednesday | 2023-06-28 | 7 | PPE156 / h | Scheduled | Main user
June | Week 26 | EXFLU | EXFLU SEB 1 | Wednesday | 2023-06-28 | 14 | PPE156 | Scheduled | Parasitic user
July | Week 27 | MONOLITH | Parasitic2022 | Wednesday | 2023-07-05 | 7 | PPE156 / i | Scheduled | Parasitic user
July | Week 27 | EP_PIXEL | run 3 | Wednesday | 2023-07-05 | 7 | PPE156 / j | Scheduled | Main user
July | Week 28 | ATLAS_HGTD | Module testing | Wednesday | 2023-07-12 | 14 | PPE146 / d | Scheduled | Parallel user
July | Week 28 | CMS_PIXEL | CMS Pixels 2023 July Run | Wednesday | 2023-07-12 | 14 | PPE156 / h | Scheduled | Main user
July | Week 30 | ALICE_ITS3 | SPS Run #2 | Wednesday | 2023-07-26 | 7 | PPE146 / f | Scheduled | Parallel user
July | Week 30 | MONOLITH | Parasitic2022 | Wednesday | 2023-07-26 | 7 | PPE156 / i | Scheduled | Parasitic user
July | Week 30 | EP_PIXEL | run 4 | Wednesday | 2023-07-26 | 7 | PPE156 / j | Scheduled | Main user
August | Week 31 | ATLAS_ITK_PIXEL | Testing of irradiated modules | Wednesday | 2023-08-02 | 7 | PPE146 / d | Scheduled | Main user
August | Week 31 | RD42 | Parasitic run | Wednesday | 2023-08-02 | 7 | PPE146 / g | Scheduled | Parasitic user
August | Week 32 | ATLAS_ITK_STRIP | Run no. 0 for Beam request in ... | Wednesday | 2023-08-09 | 7 | PPE146 / d | Scheduled | Main user
August | Week 32 | MEDIPIX | Medipix (SPS) | Wednesday | 2023-08-09 | 7 | PPE156 | Scheduled | Parallel user
August | Week 33 | ATLAS_ITK_PIXEL | Testing of irradiated modules | Wednesday | 2023-08-16 | 7 | PPE146 / d | Scheduled | Main user
August | Week 34 | MONOLITH | Run2022 | Wednesday | 2023-08-23 | 7 | PPE156 / i | Scheduled | Main user
August | Week 34 | EP_PIXEL | run 5 | Wednesday | 2023-08-23 | 7 | PPE156 / j | Scheduled | Parallel user
August | Week 35 | ATLAS_HGTD | Module testing 2 | Wednesday | 2023-08-30 | 14 | PPE146 / d | Scheduled | Main user
August | Week 35 | RD42 | Second run | Wednesday | 2023-08-30 | 7 | PPE146 / g | Scheduled | Parallel user
August | Week 35 | AIDAINNOVA_WP6 | AIDAInnova_4D | Wednesday | 2023-08-30 | 7 | PPE156 / h | Scheduled | Parallel user
September | Week 36 | CMS_PIXEL | CMS Pixels 2023 September Run | Wednesday | 2023-09-06 | 7 | PPE156 / h | Scheduled | Parallel user
September | Week 36 | PAN | High energy protons | Wednesday | 2023-09-06 | 7 | PPE156 | Scheduled | Parasitic user
September | Week 37 | PICSEL | PICSEL - MIMOSIS | Wednesday | 2023-09-13 | 7 | PPE146 / c | Scheduled | Parallel user
September | Week 37 | ATLAS_ITK_PIXEL | Testing of multiple pre-production ... | Wednesday | 2023-09-13 | 14 | PPE146 / d | Scheduled | Main user
September | Week 37 | ATLAS_AFP_TOF | AFP-ToF R&D and backup equipment test | Wednesday | 2023-09-13 | 14 | PPE156 / i | Scheduled | Parasitic user
September | Week 38 | ATLAS_BCM_PRIME | ATLAS BCM' | Wednesday | 2023-09-20 | 7 | PPE146 / g | Scheduled | Parallel user
September | Week 38 | CMS_MTD | ETL October Run | Wednesday | 2023-09-20 | 7 | PPE156 / h | Scheduled | Parallel user