## Sheet1
Ion Schedule v2.1.0 :: Beamlines T8, H2, H4 & H8 :: Status 2023-09-28 20:00 (UTC)
Schedule Run
The scheduled runs presented in this file result from applying the following filters:
Beamlines |  | Only runs which have been scheduled in either of the beamlines "H2, H4, H8, T8" are included below.
Periods |  | Only runs which belong to either of the periods "Ions 2023" are included below.
Associated Month | Associated Week | Activity | Run name | Start Weekday | Start Date | Duration [days] | Location | Status | Usage
September | Week 39 | NA61_SHINE | Pb 150 run | Monday | 2023-10-02 | 28 | PPE152 | Scheduled | Main user
September | Week 39 | PAN | Fragmented ions run | Monday | 2023-10-02 | 7 | PPE134 | Scheduled | Main user
September | Week 39 | RE44_HERD | HERD SPS ion run | Monday | 2023-10-02 | 7 | PPE134 | Scheduled | Parasitic user
September | Week 39 | VLAST | VLAST ion run | Monday | 2023-10-02 | 7 | PPE138 | Scheduled | Main user
October | Week 40 | RE44_HERD | HERD SPS ion run | Monday | 2023-10-09 | 7 | PPE134 | Scheduled | Main user
October | Week 40 | NA60+ | NA60+ detector and beam optics tests | Monday | 2023-10-09 | 10 | PPE138 | Scheduled | Main user
October | Week 41 | MEDIPIX | Medipix | Monday | 2023-10-16 | 7 | PPE134 | Scheduled | Main user
October | Week 42 | CHIMERA | EA-IRRAD ion run | Wednesday | 2023-10-18 | 12 | T8 | Scheduled | Main user
October | Week 42 | R2E | R2E irradiation | Thursday | 2023-10-19 | 6 | PPE138 | Scheduled | Main user
October | Week 42 | RE1_AMS_L0 | Charge measurement | Monday | 2023-10-23 | 7 | PPE134 | Scheduled | Main user
October | Week 43 | RE7_GAMMA_MEV | Run no. 0 for Beam request in Ions ... | Wednesday | 2023-10-25 | 5 | PPE138 | Scheduled | Main user