## Sheet1
North Area Schedule v2.1.1 :: Beamlines M2, P42-K12 and AWAKE, HiRadMat :: Status 2023-10-06 20:00 (UTC)
Schedule Run
The scheduled runs presented in this file result from applying the following filters:
Beamlines |  | Only runs which have been scheduled in either of the beamlines "K12-P42, M2, TT41, TT61" are included below.
Associated Month | Associated Week | Activity | Run name | Start Weekday | Start Date | Duration [days] | Location | Status | Usage
April | Week 17 | NA62 | NA62 Kaon | Monday | 2023-05-01 | 150 | K12-P42 | Scheduled | Main user
April | Week 17 | AMBER | Antiproton Production Cross-section ... | Monday | 2023-05-01 | 56 | M2 | Scheduled | Main user
April | Week 17 | AWAKE | AWAKE | Monday | 2023-05-01 | 21 | TT41 | Scheduled | Main user
May | Week 20 | HIRADMAT | HiRadMat run #1 | Monday | 2023-05-22 | 5 | TT61 | Scheduled | Main user
June | Week 24 | SHADOWS | Test beam 2023 | Sunday | 2023-06-18 | 11 | K12-P42 | Scheduled | Parasitic user
June | Week 25 | MUONE | Run no. 1 for Beam request in ... | Wednesday | 2023-06-21 | 14 | M2 | Scheduled | Parasitic user
June | Week 25 | AMBER | Drell-Yan Preparation | Monday | 2023-06-26 | 9 | M2 | Scheduled | Main user
July | Week 27 | NA64mu | NA64mu | Wednesday | 2023-07-05 | 7 | M2 | Scheduled | No beam (access only)
July | Week 27 | AMBER | Change over from APX to PRM measurements | Wednesday | 2023-07-05 | 7 | M2 | Scheduled | No beam (access only)
July | Week 28 | NA64mu | NA64mu | Wednesday | 2023-07-12 | 28 | M2 | Scheduled | Main user
July | Week 28 | AMBER | Change over from APX to PRM measurements | Wednesday | 2023-07-12 | 28 | M2 | Scheduled | Parasitic user
July | Week 28 | MUONE | Run no. 1 for Beam request in ... | Wednesday | 2023-07-12 | 28 | M2 | Scheduled | Parasitic user
July | Week 28 | HIRADMAT | HiRadMat Run #2 | Monday | 2023-07-17 | 5 | TT61 | Scheduled | Main user
July | Week 29 | NA62 | NA62 Dump | Thursday | 2023-07-20 | 11 | K12-P42 | Scheduled | Main user
July | Week 30 | AWAKE | AWAKE | Monday | 2023-07-31 | 14 | TT41 | Scheduled | Main user
August | Week 32 | NA64mu | NA64mu | Wednesday | 2023-08-09 | 3 | M2 | Scheduled | No beam (access only)
August | Week 33 | MUONE | Run no. 1 for Beam request in ... | Wednesday | 2023-08-16 | 9 | M2 | Scheduled | Parallel user
August | Week 33 | AMBER | PRM measurements | Wednesday | 2023-08-16 | 9 | M2 | Scheduled | Parallel user
August | Week 33 | HIRADMAT | HiRadMat Run #3 | Monday | 2023-08-21 | 5 | TT61 | Scheduled | Main user
August | Week 34 | MUONE | Run no. 1 for Beam request in ... | Friday | 2023-08-25 | 16 | M2 | Scheduled | Main user
August | Week 34 | AMBER | Change over from APX to PRM measurements | Friday | 2023-08-25 | 16 | M2 | Scheduled | Parasitic user
August | Week 34 | AWAKE | AWAKE | Saturday | 2023-08-26 | 2 | TT41 | Scheduled | Main user
August | Week 34 | AWAKE | AWAKE | Monday | 2023-08-28 | 15 | TT41 | Scheduled | Main user
September | Week 36 | AMBER | PRM measurements | Sunday | 2023-09-10 | 18 | M2 | Scheduled | Main user
September | Week 36 | MUONE | Run no. 1 for Beam request in ... | Sunday | 2023-09-10 | 18 | M2 | Scheduled | Parasitic user
October | Week 40 | AWAKE | AWAKE | Sunday | 2023-10-08 | 15 | TT41 | Scheduled | Main user